## Project Planner
GANTT - CircuitVoyager Pre1
| Plan Duration |  |  | Actual Start |  |  | % Complete |  |  |  | Actual (beyond plan) | [5 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Calendar Week | [5 empty] | Fall Holidays
[6 empty] | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Project planning & preparation | 36 | 3 | 36 | 4 | 80%
Plan Extensions Board | 39 | 1 | 0 | 0 | 0%
Schematic Extension Board | 39 | 2 | 0 | 0 | 0%
Layout Extension Board | 40 | 2 | 0 | 0 | 0%
Population and start up Extension Board | 43 | 1 | 0 | 0 | 0%
Implement external SDRAM | 41 | 2 | 0 | 0 | 0%
Implement external QSPI flash and bootloader | 42 | 2 | 0 | 0 | 0%
Implement touch display (MIPI DSI, touch) | 42 | 2 | 0 | 0 | 0%
Learn how to use TouchGFX | 44 | 1 | 0 | 0 | 0%
Misc SW implementation (LEDs, ADC, TIM) | 45 | 1 | 0 | 0 | 0%
Make the UI with pages to measure: U, I, R, C | 46 | 3 | 0 | 0 | 0%
Complete Documentation | 49 | 3 | 0 | 0 | 0%
Complete Presentation | 49 | 3 | 0 | 0 | 0%
Hand in | 51 | 1 | 0 | 0 | 0%
Documentation (Journal, Main Body) | 38 | 14 | 0 | 0 | 0%
Presentation | 38 | 14 | 0 | 0 | 0%
Fine Planning every 2 Weeks. | 38 | 14 | 0 | 0 | 0%
self rating | 51 | 1 | 0 | 0 | 0%
First milestone with meeting | 43 | 1 | 0 | 0 | 0%
Second milestone with meeting | 48 | 1 | 0 | 0 | 0%